## Product Timeline
Week | Date
1 | 2019-07-08
2 | 2019-07-15
3 | 2019-07-22
4 | 2019-07-29
5 | 2019-08-05
6 | 2019-08-12
7 | 2019-08-19
8 | 2019-08-26

## PT-Week 1
Objectives | Progress | Comments
Research different technologies, select the best one for the product.
Discover learning resources for selected technologies.
Plan product level coordination strategy. | 100% | Product level coordination has been defined. Related files can be found in Meeting 1 folder in the repo.

## PT-Week 2
Objectives | Progress | Comments
Learn the selected technologies.
Define the architecture of the projects. |  | Like MVC, using what desgin pattern, etc
Establish standards of using git commits.

## PT - Week 3
Objectives | Progress | Comments
Hold a meeting to finalize archetectures and selected technologies.
Establish base projects. |  | Project coordinators may define the extent of work that should be included in this stage. Like if there should be some views here or not.
Establish Familiarization with Azure DevOps.
Make Authroization module. |  | This includes both apps, Mechanic and User app

## PT - Week 4
Objectives | Progress | Comments
Test Authorization module.
Hold a performance evaluation and improvement meeting.

## PT - Week 5-8
These will be decided after the progress evaluation